FHA Weekly Status Report

Week Ending June 03, 2016

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling - the information modeling call for this week reviewed feedback on the three FHIM information domains distributed to the federal partners for review. Work also resumed on modeling CDS content and enhancing the FHIM model structural capabilities to support all CDS requirements identified during the previous discussions. We expect modeling of this information domain to be completed by July 1.
* Terminology Modeling - the terminology modeling call continued their process discussion related to using VSAC for the FHIM value sets repository. The group will discuss the Clinical Decision Support information domain this week, but will defer terminology work until further information modeling is complete. The group will decide on the next domain to tackle for terminology modeling on the call.
* CIMI and FHIM - the FHIM Team are participating in the CIMI WG task group meetings to develop an approach for integrating the content of the FHIM and CIMI models. This work is expected to take 6-8 weeks.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com