FHA Weekly Status Report

Week Ending December 02, 2016

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling (IM) - the IM call last week was canceled due to unavailability of key participants. The group will continue modeling discussions concerning enhancing the FHIM model structural capabilities to support all CDS requirements and integration with CIMI this week addressing the areas of observations and providers. We expect this work to be completed between 12/16 and 12/31/2016.
* Terminology Modeling (TM) - the TM call last week was canceled due unavailability of the lead modeler. On the call this week, we expect to complete work on the Patient Education information domain and begin modeling the Eligibility, Enrollment and Coordination of Benefits (EECOB) information domain. We expect the EECOB work to be completed by 1/31.
* Prototyping of approaches to integrate CIMI and FHIM and support the FHIR information exchange format continued last week on the CIMI calls and the Friday information modeling calls. This work is estimated to be completed by 1/27/17. Updates on the progress of prototyping efforts will be provided on the Managing Board calls.
* Proposals to conduct pilot tests for integrating FHIM, CIMI, SOLOR and CQF models continue to be developed. A proposal has been submitted to the DOD/VA IPO to establish a Joint Incentive Fund (JIF) pilot test project. A decision on this proposal should be made in January 2017. Further updates on work in this area will be provided on the Managing Board calls.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com