FHA Weekly Status Report

Week Ending December 16, 2016

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling (IM) - the IM call last week continued modeling discussions concerning enhancing the FHIM model structural capabilities to support all CDS requirements and integration with CIMI. We expect the discussions to be completed between 12/16 and 12/31/2016 and the restructuring of the FHIM to begin. The FHIM restructuring should be completed by 1/31.
* Terminology Modeling (TM) - the TM call last week began modeling the Eligibility, Enrollment and Coordination of Benefits (EECOB) information domain. This work will continue this week. We expect the EECOB work to be completed by 1/31.
* Prototyping of approaches to integrate CIMI and FHIM and support the FHIR information exchange format continued last week on the CIMI calls and the Friday information modeling calls. This work is estimated to be completed by 1/27/17. Updates on the progress of prototyping efforts will be provided on the Managing Board calls.
* Proposals to conduct pilot tests for integrating FHIM, CIMI, SOLOR and CQF models continue to be developed. A proposal has been submitted to the DOD/VA IPO to establish a Joint Incentive Fund (JIF) pilot test project. A decision on this proposal should be made in January 2017. Further updates on work in this area will be provided on the Managing Board calls.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com