FHA Weekly Status Report

Week Ending March 11, 2016

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling - the information modeling call for this week was used to prepare three information domains for distribution to the federal partners. Modeling of the Clinical Decision Support information domain will resume next week. We expect modeling of this information domain to take another 3-3 1/2 months.
* Terminology Modeling - the terminology modeling call for this week was focused on preparing three information domains for distribution to the federal partners. Modeling of the General orders information domain will resume next week. We expect this modeling to take another 5-6 weeks.
* CIMI and FHIM - the FHIM Team continued analyzing CIMI and the potential integration of the FHIM and CIMI models on the CIMI WG weekly call. We are receiving very good feedback from the CIMI WG and other WGs at HL7. This analysis will probably take another 4 weeks. The integration that we believe is feasible is to integrate the content of the two models, not the models themselves. So the CIMI content would be integrated with the FHIM content to extend the detail of the FHIM and all of this content would be leveraged by MDHT in generating platform specific implementation models (e.g., CDA, FHIR, NIEM, etc.).
* The FHIM Team is preparing three FHIM information domains for distribution to the federal partners for review and feedback. The three domains are Care Plans, Medications/Pharmacy and Imaging/Radiology. The estimated timeframe for distribution of the domains is March 18. Federal partners will have a month to review the domains and submit their feedback.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com