FHA Weekly Status Report

Week Ending January 20, 2016

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling (IM) - the IM call last week was canceled due to the HL7 meeting. Modeling work on the structural integration of CIMI and FHIM will resume this week. Discussions concerning the integration of CIMI and FHIM also continued at the HL7 meeting last week. We expect the discussions to be completed by 1/31 and the FHIM restructuring should be completed mid-February.
* Terminology Modeling (TM) - the TM call for last week was canceled due to the HL7 meeting. We will continue modeling the Eligibility, Enrollment and Coordination of Benefits (EECOB) information domain this week. We expect the EECOB work to be completed by mid-February.
* Prototyping of approaches to integrate CIMI and FHIM and support the FHIR information exchange format continued last week at the HL7 meeting. This work is estimated to be completed by mid February. Updates on the progress of prototyping efforts will be provided on the Managing Board calls.
* Proposals to conduct pilot tests for integrating FHIM, CIMI, SOLOR and CQF models continue to be developed. A proposal has been submitted to the DOD/VA IPO to establish a Joint Incentive Fund (JIF) pilot test project. A decision on this proposal should be made by the end of January 2017. Further updates on work in this area will be provided on the Managing Board calls.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com