FHA Weekly Status Report

Week Ending April 07, 2017

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling (IM) - the IM call last week continued work on updating the Security information domain. This work will continue this week and should be completed by 4/30. The FHIM team continued participating in CIMI weekly calls. Further work on CIMI and FHIM harmonization will be accomplished as CIMI harmonizes with FHIR and further defines CIMI structures.
* Terminology Modeling (TM) - the TM call for last week addressed pending items related to Immunizations and Allergies. This week we will complete the work started last week and begin work on the Security information domain.
* Proposals to conduct pilot tests for integrating FHIM, CIMI, SOLOR and CQF models continue to be pursued. We are exploring pilot testing with VA and DoD and with the ONC PCOR initiative. Updates on the progress of pilot test efforts will be provided on the Managing Board calls.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com