FHA Weekly Status Report

Week Ending August 03, 2018

**Company Name:** Apprio Inc.

**ONC Client Name:** ONC, FHA

**ONC Individuals Supported:** Gail Kalbfleisch, Cheryl Madlansacay, John Forrester

**Accomplishments:**

* Information Modeling (IM) - the IM call last week discussed the HSPC/CIIC meeting and completed a discussion about order actions that was not completed on the call last week. The call this week will look at the USCDI data domains and begin modeling the Clinical Documents domain, which includes clinical notes.
* Terminology Modeling (TM) - the TM call last week was canceled due to the lead modeler being on vacation. The TM call this week will resume modeling the Skin and Wound Assessment domain.
* The FHIM presentations for NLM and HHS CIO Office are undergoing final review by the FHA leads.

**New Risks Identified and Mitigation/Resolution Recommendations:**

# Comments/Remarks:

# Point of Contact:

**Name:** Steven Wagner

**Telephone:** 603-624-5942

**E-mail:** swagner@apprioinc.com