## Slide 1: Health Information Modeling WG
Purpose: Develop information and implementation models to fully support health interoperability and harmonize information from the individual federal partners and standards organizations into a single, logical, health information model that can be used as the basis for a model driven architecture (MDA) approach to generating interoperability specifications.
Target: Fully integrate the FHIM into the S&I Framework process and develop interoperability specifications using the MDA approach to support MU and other federal partner use cases
Recent/Upcoming Deliverables:
  Finish mapping FHIM to all ongoing S&I Framework initiatives (11 of 13 completed): estimated completion May 2015
  Begin second effort integrating FHIM into S&I Framework: est. completion June 2015 (Dependent on availability of S&I Framework resources)
  Released three FHIM information domains (Allergies, Health Concern, Vital Signs) for partner review/comment/validation. Feedback due 6/26.

## Slide 2: Health Information Modeling WG
 | FEDERAL PARTNERS PROBLEM STATEMENT
 | Develop information and implementation models to fully support health interoperability and harmonize information from the individual federal partners and standards organizations into a single, logical, health information model that can be used as the basis for a model driven architecture (MDA) approach to generating interoperability specifications.
 | REQUESTORS: VA, DoD
 | CHALLENGES
 | Obtaining broad participation/input from the federal partners Fully integrating the FHIM into the S&I Framework process and maximizing its efficient use Standardizing the process and tools for modeling business use cases Obtaining sufficient FHA or in-kind federal partner resources to accomplish all the work required to achieve goals Hot Button Issue Integration of FHIM into S&I Framework going slowly. First effort did not complete task. Second effort about to start. Support for mapping S&I Initiatives to FHIM seems to have dried up.
 | TARGETS/GOALS
 | Fully integrate the FHIM into the S&I Framework process Interoperability specifications using the MDA approach to support MU and other federal partner use cases
ACTION PLAN
DELIVERABLES
Harmonized, logical information model (FHIM) (est. 2.5 years to complete modeling all domains) Interoperability specifications
 | Action | Date
 | Model at least one additional information domain per quarter (51% complete) | Quarterly
 | Model terminologies and define value sets to support each information domain modeled in previous action item (32% Complete) | Quarterly
 | Finish mapping all ongoing S&I Framework initiatives to FHIM (85% complete) | Ongoing Est. Completion MAY 15
 | Integration of FHIM into the ongoing S&I Framework process | JUNE 2015 S&I Dependent
 | Produce interoperability specification for S&I Framework using the MDA process (Dependent on completion of action item above) | S&I Dependent
 | Support evaluation of FHIM by DAF/SDC/CQF Tiger Team to support their information modeling requirements | S&I Dependent
= On Target
= “Go Faster”
= Not Started
= Late/Problem Area
= Complete