## Slide 1: Health Information Modeling WG
Federal Partners Problem Statement
Requestors
DOD, VA
Challenges:
Obtaining broad participation/input from the federal partners
Fully integrating the FHIM into the S&I Framework process and maximize its efficient use
Standardizing the process and tools for modeling business use cases
Obtaining sufficient FHA or in-kind federal partner resources to accomplish all the work required to achieve goals
Hot Button Issue
Integration of FHIM into S&I Framework going slowly. First effort did not complete task. Second effort about to start.
Support for mapping S&I Initiatives to FHIM seems to have dried up.
Targets/Goals
Fully integrate the FHIM into the S&I Framework process
interoperability specifications using the MDA approach to support MU and other federal partner use cases
Federal Partners Action Plan
Deliverables
Harmonized, logical information model (FHIM) (est. 3 years to complete modeling all domains)
Interoperability specifications
Action | Date
Model at least one additional information domain per quarter (18 of 37 modeled, 1 underway, 18 to be modeled) | Quarterly
Model terminologies and define value sets to support each information domain modeled in previous action item | Quarterly
Finish mapping FHIM to all ongoing S&I Framework initiatives (10 of 13 completed) | Ongoing
Integration of FHIM into the ongoing S&I Framework process | 31 Mar
Produce interoperability specification for S&I Framework using the MDA process (Dependent on completion of action item above) | S&I Dependent
Develop information and implementation models to fully support health interoperability and harmonize information from the individual federal partners and standards organizations into a single, logical, health information model that can be used as the basis for a model driven architecture (MDA) approach to generating interoperability specifications.
= Complete = On Target = “Go Faster” = Late/Problem area = Not Started
Support evaluation of FHIM by DAF/SDC/CQF Tiger Team to support their information modeling requirements | S&I Dependent