## Slide 1: UPDATE: FEDERAL HEALTH INFORMATION MODEL TRANSITION
Steve Wagner, FHA

## Slide 2: FHIM Transition
FHIM project kickoff meeting was held to review updated SOW for new FHIM contract year (8/21/2018 to 8/20/2019)
  Two potential transition organizations were identified - Open Group and HL7
  A draft work plan for the SOW tasks was reviewed and updated
  Further work will be completed on FHIM/USCDI mapping/support for 2019 and 2020 USCDI domains
  A FHIM HL7 ballot is being explored
Terminology modeling of the “Skin and Wound Assessment” domain was completed
All FHIM artefacts will be maintained in the open source GitHub repository through the end of the contract
The fhims.org web site will be updated to add full support for the terminology and implementation modeling work streams and enhance support for the information modeling work stream
Progress
Link to Backup Slides
Notes: For more information on the CIMI/FHIR profiles, please see the back up slide deck located here:

## Slide 3: FHIM Transition
FHIM support ends 20 AUG 2019
31 OCT 2018: Determine most appropriate organization for FHIM transition
30 Nov 2018: The FHIM team will finalize value set bindings for all FHIM value sets
Call to Action
Next Steps
Link to Backup Slides